## Sprint Backlog
ID | Task | Type | Priority | Owner | Start Date | End Date | Status
SP-01 | Implement book catalog API (list + detail) | Backend | High | BE | 29/01/2026 | 30/01/2026 | To Do
SP-02 | Build book catalog UI (user view) | Frontend | High | FE | 29/01/2026 | 31/01/2026 | To Do
SP-03 | Implement search & filter (title, category) | Backend | High | BE | 31/01/2026 | 01/02/2026 | To Do
SP-04 | Integrate search & filter UI | Frontend | High | FE | 01/02/2026 | 02/02/2026 | To Do
SP-05 | Create borrow transaction endpoint | Backend | High | BE | 03/02/2026 | 04/02/2026 | To Do
SP-06 | Validate stock availability on borrow | Backend | High | BE | 04/02/2026 | 05/02/2026 | To Do
SP-07 | Auto update stock after borrow | Backend | High | BE | 05/02/2026 | 05/02/2026 | To Do
SP-08 | Build admin borrowing approval UI | Frontend | High | FE | 06/02/2026 | 07/02/2026 | To Do
SP-09 | Implement approve/reject borrowing flow | Backend | High | BE | 07/02/2026 | 08/02/2026 | To Do
SP-10 | Implement return book flow + return date | Backend | High | BE | 09/02/2026 | 10/02/2026 | To Do
SP-11 | Auto restore stock after return | Backend | High | BE | 10/02/2026 | 10/02/2026 | To Do
SP-12 | Role-based access control (user/admin) | Backend | High | BE | 11/02/2026 | 11/02/2026 | To Do
SP-13 | Prevent unauthorized access (ID tampering) | Security | Medium | BE | 11/02/2026 | 11/02/2026 | To Do
SP-14 | Blackbox testing core borrowing flow | QA | Medium | QA | 12/02/2026 | 12/02/2026 | To Do
SP-15 | Bug fixing & regression test | QA | Medium | QA | 12/02/2026 | 12/02/2026 | To Do